## Sheet1
Numb | What | Details | Who | From | To | Comments | Deliverbales
1 | Service Strategy Scope | Draft the service profile and details for the both service provided | Mayar | 8.1.2026 | 15.1.2026 | * Focus on influencing Marketing/ Digital Existence Focused * Add the Schools Offline penetration as part of the offline recommendations
1.1 | Services Detailed Proposition | Draft out the details of the service pillars that shall be delivered | Mayar | 8.1.2026 | 15.1.2026
1.2 | Service Survey | * Draft service survery * Translate The Survery | Mayar Asmaa | 10.1.2026 | 11.1.2026
1.2.1 |  | Share the survey with different participate and track the results | All team | 12.1.2026 | 14.1.2026
1.2.2 |  | Survery Analysis | Sherry | 14.1.2026 | 15.1.2026
1.2.3 |  | Results sharing and recommendations review | Sherry
1.3 | SWOT & PESTEL Analysis | * Conduct SWOT Analysis * Conduct PESTEL Analysis | Asmaa & Sherry Mohamed | 11.1.2026 | 14.1.2026
2 | Buyer Persona | Develop Service Buyer Persona | Asmaa Shrouk | 8.1.2026 | 12.1.2026 | Shrouk: Reiew the Customer Proposed + other buyer persona proposed * Add parents as targeted/ Buger Persona Segment in the following 1- Thanaweya Amma 2- Students in Colleges.
3 | Competitor Analysis | Research on the 4 Competitors related to the taregted segment | Mahaba Sherry | 8.1.2026 | 12.1.2026 | Mahaba: Review Followers + Engagement Rate
4 | Service Strategy SOSTAC Model | Full Service Direction indentification | Mohamed | 8.1.2026 | 10.1.2026 | Shall need to review all these insights after completion and determine what needs amending on the strategy scope
4.1 | Service Startegy Execution Roadmap in Q1 2026 | * Offline & Online Endeavors Objectives Determination, HOW, When Full Plan *Revamp the SOSTAC into a bigger, more detailed oriented scope with action plan on each step, timeframes and KPI's | Mayar | 15.1.2026 | 17.1.2026 | Need SWOT & PESTEL Findings
5 | Content Strategy ( Goals & Objectives & Execution Milestones) | Create the online content strategy, goals, Objectives and KPI's | Sherry Mayar | 17.1.2026 | 18.1.2029
6.1 | Digital Presence Initiation | Design Visuals (Logo, Cover Photo,…etc) | Mahaba Shrouk | 12.1.2026 | In Progress
6.2 |  | Design Social Media Agreed on Pages (Instagram, Facebook) | Mayar | 18.1.2026 | 19.1.2026
6.3 |  | Editing the Pages Initial Info ( Bio, About)
6.4 |  | Design Social Media Calendar on the segmented platforms | Mahaba | 18.1.2026 | 19.1.2026
6.5 |  | Create Posts, Reels, Events, …... Etc and post them on pages | Mahaba Shrouk | 12.1.2026 | 19.1.2026
7 | Wrap Up & Recommendations | Review all deliverables and finetune | Mayar | 14.1.2026 | 20.1.2026
8 | عمل العرض التقديمي للمشروع | عمل العرض التقديمي للمشروع و تسليمه | Mohamed | 25.1.2026 | 27.1.2026
9 | عمل بوست Awareness/CTA لعمل مستهدف ال Traffic عليه | عمل بوست للنزول علي المنصتين يدعم دخول المتصفح علي رسال الفيس بوك و الانستجرام للاستفسار عن الخدمة | NA | 26.1.2026 | 27.1.2026 | تم استخدام محتوي سابق عمله/ لم يتم عمل محتوي جديد و ربطه بالمستهدف المطلوب
9.1 | عمل الحساب المالي علي ال Meta Business Suite | تفعيل الحساب المالي دون اضافة اي رصيد مالي | Mayar Sherry Asmaa | 27.1.2026 | 27.1.2026
9.2 | عمل اضافة للمستهدف ال Traffic علي Meta suite | عمل كل الخطوات الخاصة باضافة المستهدف Traffic و عمل الحملة الدعائية عليه | Mayar Sherry Asmaa | 27.1.2026 | 27.1.2026
9.3 | تفعيل الحملة الدعائية و عمل Screenshots مبدية للتفعيل للعرض في تقرير العرض التقديمي | تفعيل الحملة الدعائية و عمل Screenshots مبدية للتفعيل للعرض في تقرير العرض التقديمي | Mayar | 28.1.2026 | 28.1.2026
9.4 | قياس ال Insights | قياس ال Insights | Mayar | 30.1.2026 | 30.1.2026
10 | Awareness Objective Execution
10.1 | Update about the awareness campaigns/Gap Vs Expected | Scale down the current requirement for the Awareness phase to be full aligned during the time from 9.3.2026 to 31.3.2026 | Mayar | 9.3.2026 | 9.3.2026 |  | Sent on WhatsApp Group
10.2 | Send proposed Content Calendar & Modify | Team Review proposed content Plan for the upcoming month (Awareness Directed & Traffic Intro) | Mayar (All Team Review) | 9.3.2026 | 9.3.2026 |  | Sent on WhatsApp Group
10.3 | Agree on Content Calendar Plan | Provide modification to finetune Content Calendar with content strategy direction | All team | 9.3.2026 | 11.3.2026 | If by 11.3.2026 no comment is made, this is considered agreement on the content calendar direction and content to be executed and distributed to teams accordingly.
10.4 | Content Development Small Groups Distribution | Divide team members to cascade the execution of the agreed content calendar | All team | 9.3.2026 | 9.3.2026
10.4.1 | Team A: Sherry & Shrouk | Content & Visual | All team | 9.3.2026 | 9.3.2026
10.4.2 | Team B: Asmaa & Mahaba | Content & Visual | All team | 9.3.2026 | 9.3.2026
10.4.3 | Team C: Mohamed & Mayar | Content & Visual | All team | 9.3.2026 | 9.3.2026
10.5 | Activate Content Calendars | Divide the content pieces agreed on across the month on all team, agree on each team deliverables and timelines for both review, submission and posting on agreed on platforms | All team | 11.3.2026 | 11.3.2026 | During Meeting from 8-9 for all team to agree on timelines.
10.5.1 | Group 1 Post Execution | Deliver Post 1/Carasoul visuals & Caption and post them | Mayar & Mohamed | 11.3.2026 | 12.3.2026 | Done
10.5.2 | Group 2 Post Execution | Deliver Post 1/Reel & Caption and post them | Shrouk & Sherry | 13.3.2026 | 14.3.2026 | Done
10.5.3 | Extra Social Content Creation | Creation for 2 content: Mothers day reel & Eid Celebration Interactive content to be posted during these intervails | Shrouk | 12.3.2026 | 14.3.2026 | Done & Team Approved to publish
10.5.4 | Group 3 Post Execution | Deliver Post 3/ Either Reel or Carasoul with voice & Caption and post them | Mahaba & Asmaa | 14.3.2026 | 16.3.2026 | Done
10.5.5 | Post Eid El Fitr Interactive content | Post Eid El Fitr Interactive content on both platforms wirh caption | Shrouk | 19.3.2026 | 19.3.2026 | In Progress
10.5.6 | 1st Paid Ad Campaign | Create Awareness Goal Setting for the 1st Paid Ad Campaign/ Mohters Day Campaign | Mohamed + Asmaa | 19.3.2026 | 20.3.2026 | In Progress

## Sheet2
Name | DEPI Email
Shrouk Zaki | shroukmohammed500@gmail.com
mohamed elnahas | schwinghyd@gmail.com
Asmaa Saeed Ali Ali Elmezayen | asmaa89.edu@gmail.com
Mahaba william | mahabafady@gmail.com
Sherry Mikhael Lobous | sherrymikhael97@gmail.com