## 6- Service Startegy Execut.Plan
Study Abroad Strategy Execution Plan for Q1 & 2 2026
Pillar | Department | Start Date | End Date | Deliverables
Phase 1: Foundation & Readiness (Q1 2026) |  |  |  | * Service Detailed Description. * Consultation Packages Pricing Ranges Profiles.
Focus: Infrastructure, messaging clarity, internal alignment
Key Actions
Finalize service packages and pricing per each pillar ( Consulting & Facilitation Packages). | Operations & Supply Chain | 1.2026 | 3.2026
Align value proposition to each buyer persona | Strategy
Standardize consultation journey (lead → call → proposal → follow-up) | CRM
Select Tracking System & Set it out + Test before activation | IT
Prepare service detailed descriptions, FAQ's. | Online Technical Support
Phase 2: Awareness & Insights Review (Q2 2026) |  |  |  | * Social Media Calendar for Q1 & Q2 * Posts on SM platforms * Insights tracking and follow-up * Conversion reports and optimization insights
Focus: content scaling and awareness.
Key Actions
Launch always-on content engine (organic + paid) as per the social media content calendar | Social Media Team | 2.2026 | 5.2026
Activate partnerships (schools, counselors, influencers) | Strategy & Partnership
Plan offline Exhibitions ( Venue, Targets, Scale, Numbers, Advertising method, …). | Strategy & Operations
Introduce webinars / virtual info sessions | Social Media Operation